## Sheet1
Topic ID | Topic Name | Topic Desc | URL 01 | URL_01_Locked | URL 02 | URL_02_Locked | URL 03 | URL_03_Locked | URL 04 | URL_04_Locked | Doc 01 | Doc_01_Locked | Doc 02 | Doc_02_Locked | Doc 03 | Doc_03_Locked | Doc 04 | Doc_04_Locked | Active | Deleted | ChangeLog
1 | An Introduction to Using Project 2013 | Welcome to the first lesson of "Microsoft Project 2013 for Beginners" series. This course is intended to those who have never used MS Project before but who are already familiar with the basics, those who have been using the older versions or recent versions of MS Project, or even those who have never heard of MS Project before. Over time, some principles of MS Project have changed a bit, and in MS Project 2013 version, there have been many additions and functional changes. Microsoft has tried to make the product usable with touch screen too. In this first part of the course, find out how to install Project 2013 on your computer or handheld device to get you started. | https://www.youtube.com/embed/ZFPy5XvxG0g | Yes | https://www.youtube.com/embed/9RdBMoy-Ty0 | Yes |  |  |  |  | http://www.tutorialspoint.com/plsql/plsql_arrays.htm | Yes | [6 empty] | Yes | No | New Record
2 | What's New in Microsoft Project 2013 | Let's get started with Microsoft Project 2013 first by getting acquainted with its new and improved features. First off, MS Project 2013 provides links not only to creating a new blank project, but also links to project templates and other facilities that would allow you to import information from MS Excel or Sharepoint. Another area of improvement in MS Project 2013 is in the range of reports. | https://www.youtube.com/embed/Npf1VWhCqkY | Yes | https://www.youtube.com/embed/DDtiQFat-gI | Yes |  |  |  |  | http://www.tutorialspoint.com/plsql/index.htm | Yes | [6 empty] | Yes | No | New Record
3 | MS Project 2013: Project Help Facilities | This video explains about help facilities in Microsoft project for those who are new to Project. To get help about particular features of MS Project 2013, there are two ways of pulling up the Project Help tool--either click the question mark icon or press the F1 keyboard shortcut. Some of the features of Help in Project 2013 are the Getting Started section, the What's New with Project 2013 section, and Basic Tasks in Project. | https://www.youtube.com/embed/MRgt1hD9gCE | Yes | [6 empty] | http://www.tutorialspoint.com/plsql/plsql_overview.htm | Yes | [6 empty] | Yes | No | New Record
4 | MS Project 2013: Start Screen, Workspace, Backstage View | This video explains about having the Start screen enabled and a lot of customization that's possible with the Project Workspace. Some of the features of the Start screen in MS Project 2013 are Blank project, New from existing project, New from Excel workbook, New from SharePoint Tasks List, Welcome to Project, and Software Development Plan. Also discusses about all the dialogs which appear in backstage view such as Save,open,options,schedule. | https://www.youtube.com/embed/7oXikkaeyv0 | Yes | https://www.youtube.com/embed/3x0OBF6pvmQ | Yes |  |  |  |  | http://www.tutorialspoint.com/plsql/plsql_environment_setup.htm | Yes | [6 empty] | Yes | No | New Record
5 | MS Project 2013: Touch Device | Microsoft has recognized that one of the key issues with using a touch device is the accuracy of touching part of the screen, particularly for those with fairly fat fingers. There are several articles in Microsoft.com that provide guidelines with some particular issues such as targeting a specific point on the screen. There are also user interface elements such as the color picker, the general principle of which is to take the conventional color picker and just make everything bigger so that it would be easier to operate with your fingers. Learn how to zoom in and zoom out using your fingers. | https://www.youtube.com/embed/2mXc7Ufxr9M | Yes | [6 empty] | http://www.tutorialspoint.com/plsql/plsql_environment_setup.htm | Yes | [6 empty] | Yes | No | New Record
6 | MS Project 2013: How to Navigate the Ribbon in Project | The Ribbon is a rectangle at the top of the window with a number of symbols on it, and the symbols represent different kinds of commands, options, buttons, settings, and so on. There's a Task tab, Resource tab, Report tab, Project tab, and View tab. On every tab, there are groups, and each group has a number of commands. There is also what we call contextual tabs or those that appear only in certain circumstances. Some commands are enabled while some are disabled or greyed out. When you have been using Project 2013 for a while, you might come to a moment when you would like to put the ribbon away to give you a lot more space to work in. Or perhaps you'd like to customize the ribbon. Find out how to do these and learn more about the ribbon in this video. | https://www.youtube.com/embed/V8z-FWCN7h0 | Yes | https://www.youtube.com/embed/tP9rPXgCsOw | Yes |  |  |  |  | http://www.tutorialspoint.com/plsql/plsql_data_types.htm | Yes | [6 empty] | Yes | No | New Record
7 | MS Project 2013: How to Use the Quick Access Toolbar | The Quick Access Toolbar is at the top left-hand corner of the window, the purpose of which is to give quick access to a selected small number of commands that people use frequently and really want at their fingertips so that they can execute them quickly and easily whenever they need them. The Quick Access Toolbar is of course customizable, and there are plenty of commands to choose from. You can add more commands to the toolbar. In the same way, you can also remove commands from the Quick Access Toolbar. | https://www.youtube.com/embed/vKo1gGo_nvw | Yes | https://www.youtube.com/embed/IEh3_dh3KOk | Yes |  |  |  |  | http://www.tutorialspoint.com/plsql/plsql_constants.htm | Yes | [6 empty] | Yes | No | New Record
8 | MS Project 2013: How to Use the Mini Toolbar in Project | Many people prefer using the Mini Toolbar to using the Ribbon, and particularly if you collapse the Ribbon, the mini toolbar would mean that you rarely need to go near the Ribbon. The Mini Toolbar can be used both in mouse mode and touch mode, They tend to have a lot of commands in common, but there are usually some differences between the ones you get with mouse and the ones you get with touch. In a nutshell, the Mini Toolbar gives a very quick way of accessing important commands, such as changing the font style or the font size, making the text bold or italic, or coloring the text, and so on. | https://www.youtube.com/embed/jWXKrZeXnfU | Yes | [6 empty] | http://www.tutorialspoint.com/plsql/plsql_operators.htm | Yes | [6 empty] | Yes | No | New Record
9 | MS Project 2013: Using Contextual Menus | This video explains how contextual menus work using mouse and using touch. Depending on where you are and what you are doing, the menu displays a set of commands that are relevant to the view you are in and what you can possibly do at that point. In some instances, some commands may be grayed out and are unusable. For example, if you go into Gantt Chart View, you get a completely different set of commands than when you are in Network Diagram View, and vice versa. | https://www.youtube.com/embed/u5BNLNLS8ME | Yes | [6 empty] | http://www.tutorialspoint.com/plsql/plsql_conditional_control.htm | Yes | [6 empty] | Yes | No | New Record
10 | MS Project 2013: Understanding the Status Bar | The Status Bar is found at the bottom of the window. If you right click on the Status Bar, it brings up a menu that displays a bunch of properties such as Cell Mode, Calculation, Macro Recording, Filter, and AutoFilter. And it is up to you to decide which ones you want to show on the Status Bar and which ones you don't want to show on the Status Bar. At the right-hand end of the Status Bar are a set of buttons that you can use to switch between views of your current project. Project 2013 has different views available, which include Gant Chart View, Task Usage View, Team Planner View, Resource Sheet View, and Report View. | https://www.youtube.com/embed/cQT1q2zVvag | Yes | [6 empty] | http://www.tutorialspoint.com/plsql/plsql_loops.htm | Yes | [6 empty] | Yes | No | New Record
11 | MS Project 2013: How to Setup General Options in Backstage View | In the General Options page of Project 2013, you have the User Interface Options that would let you choose whether or not to show feature descriptions in ScreenTips. You can also change the Project View, Personalize your copy of Microsoft Office by typing in your preferred username and initials, or change the Office Background and Office Theme. One of the key strengths of Microsoft Project is its ability to take information about the work that needs to be done and to come up with a schedule that satisfies all of the constraints that you put on it. The constraints will include things like how long each task is, how much work is involved, what resources you’ve got available, people, rooms, machinery, and more! Find out how auto scheduling works compared to manual scheduling. | https://www.youtube.com/embed/_PC1wSEPvCA | Yes | https://www.youtube.com/embed/bbBIbCY4E1U | Yes |  |  |  |  | http://www.tutorialspoint.com/plsql/plsql_arrays.htm | Yes | [6 empty] | Yes | No | New Record
12 | MS Project 2013: Creating a Project Containing Summary Task Requirements | This video explains how to create a project and how to collect the summary task requirements of a project using Microsoft Project 2013. | https://www.youtube.com/embed/FZyCjPc0CRQ | Yes | https://www.youtube.com/embed/1zccQ1Nfd8w | Yes | https://www.youtube.com/embed/L_31yTIjXao | Yes |  |  | http://www.tutorialspoint.com/plsql/plsql_constants.htm | Yes | [6 empty] | Yes | No | New Record
13 | MS Project 2013: Adding Project Information to Your Project | One of the important things that you need to consider when using Microsoft Project 2013 is the Project Information. Here you can set the project start date as well as the project finish date. The Project Information tool helps you to schedule the work on your project to enable you to finish it as quickly as possible. For example, when building a house, you'd want to finish building it as soon as possible in order to get the house on the market, sell it, and earn money for it. Each project uses the standard calendar by default, but there can also be multiple calendars associated with a project. | https://www.youtube.com/embed/Qy9Q_iNwstY | Yes | [6 empty] | http://www.tutorialspoint.com/plsql/plsql_operators.htm | Yes | [6 empty] | Yes | No | New Record
14 | MS Project 2013: How to Setup Tasks | This video explains about the task of building a house using a blank project, among other equally important basic features of MS Project 2013.Starting from a very simple house model that slowly morphs into one with added functional features. In this example, the entire process--from entering a task, indicating the duration of each task, setting the project start date, up to saving the project is covered. There are also other pieces of information that are automatically entered by Project as you are setting up the tasks in your project, and one of them is Task Mode, which could either be Auto Scheduled or Manually Scheduled. There's also an ID number given to every task entered. | https://www.youtube.com/embed/KQzt4QCXIEQ | Yes | https://www.youtube.com/embed/PdQVwQmNJOQ | Yes |  |  |  |  | http://www.tutorialspoint.com/plsql/plsql_conditional_control.htm | Yes | [6 empty] | Yes | No | New Record
15 | MS Project 2013: Project Options, Timeline, Advanced Properties | This video explains about Project Options, which can be accessed from Backstage View. The Scheduling Options page allows you to choose whether to auto schedule a task or not, and if you do, you can either set it to project start date or current date. Meaning if you enter an auto scheduled task and you chose current date, the task will be scheduled to begin on the date that you are actually entering the task. The duration of each task can either be minutes, hours, days, weeks, or months, as the case may be. If you want to save some space when working on a project, you can also switch off the timeline, especially if you are not going to be using it for the moment. Another useful tool is Advanced Properties where you can set some properties that are more related to the file that you are working on. | https://www.youtube.com/embed/06lzcRpVuDs | Yes | https://www.youtube.com/embed/On3spbR41ms | Yes |  |  |  |  | http://www.tutorialspoint.com/plsql/plsql_loops.htm | Yes | [6 empty] | Yes | No | New Record
16 | MS Project 2013: Setting Up Dependencies Between Tasks in Project | This video explains about creating task dependencies (links) within your project and After tasks are created in a project, they need to be linked to show relationships between them. Linking tasks creates task dependencies. Also shows the relationships between multiple projects by linking tasks across projects, or by using inter-project dependencies. You can link tasks within the same project by using the Gantt Chart view, the Network Diagram view, or the Calendar view. | https://www.youtube.com/embed/hbvKEi0JG58 | Yes | https://www.youtube.com/embed/__5aBo-mzsU | Yes |  |  |  |  | http://www.tutorialspoint.com/plsql/plsql_arrays.htm | Yes | [6 empty] | Yes | No | New Record
17 | MS Project 2013: Resource Basics,How to Setup Resources in Project | In Project 2013, there are three types of resources: Work, Material, and Cost. Work refers to the people who are working on the project such as laborers, bricklayers, painters, and so on. Materials are the things that get consumed in the building of the house, which include bricks, window frames, concrete cement, mortar, and so on. An example of Cost is an account for various expenses such as a petty cash account for travel expenses, and so on. This lesson generally revolves around these types of resources, and demonstrates how each type is set up properly. Find out how to use the Resource Information dialog and the Task Information dialog with the different tabs such as General, Costs, Notes, and Custom Fields. | https://www.youtube.com/embed/ByKkTvVCQJo | Yes | https://www.youtube.com/embed/f2wxhtXFfH4 | Yes |  |  |  |  | http://www.tutorialspoint.com/plsql/plsql_constants.htm | Yes | [6 empty] | Yes | No | New Record
18 | MS Project 2013: How to Assign Resources in Microsoft Project | Resource assignment is basically the process of assigning a list of resource names to various tasks in a certain project. In given example, it is a building project. But what if you have a long list of resources? It would be fairly difficult to find the specific resource you are looking for. Good thing the Assign Resources dialog in Project 2013 has filter facilities, which always come in handy in this part of the lesson. Also demonstrates how to allocate resources--like bricklayer, bricks, carpenter, door, window, etc.--into their corresponding tasks and shows us how these resource assignments impact the Gantt Chart. | https://www.youtube.com/embed/BHRgMaGk9F0 | Yes | https://www.youtube.com/embed/h7n2rkdiLIA | Yes |  |  |  |  | http://www.tutorialspoint.com/plsql/plsql_operators.htm | Yes | [6 empty] | Yes | No | New Record
19 | MS Project 2013: Opening and Closing Projects | There are many ways in opening projects. One of which, as discussed in previous sections, is by clicking Recent Projects in Backstage View. However, if the project you are looking for is not in the Recent Projects list, another way to open it is to click Open Other Projects in which Project 2013 displays potential locations for a project that you want to open--either from SkyDrive or Computer. Another way to open a project is through the Browse button, which allows you to select from your available disc drives, internal disc drive, memory sticks, or network drives. So let's say you have your project open. Suppose you need to open another project and have both projects open at once? That's not a problem! The switching facility of Windows will take care of it. Now to close a project or projects, there are various ways to do that--in Backstage View or through the Ribbon. | https://www.youtube.com/embed/xHQqTLnujOE | Yes | [6 empty] | http://www.tutorialspoint.com/plsql/plsql_conditional_control.htm | Yes | [6 empty] | Yes | No | New Record
20 | Microsoft Project 2013: Critical Paths | In this video, discover the meaning and importance of critical paths using Microsoft Project 2013. | https://www.youtube.com/embed/F1r7h15ngJw | Yes | https://www.youtube.com/embed/XMXjmv5O0VI | Yes |  |  |  |  | http://www.tutorialspoint.com/plsql/plsql_loops.htm | Yes | [6 empty] | Yes | No | New Record
21 | Microsoft Project 2013: Scheduling | In this video, discover the different factors that affect the schedules of various tasks and resources in Microsoft Project 2013. | https://www.youtube.com/embed/gV-wpY8AnA4 | Yes | [6 empty] | http://www.tutorialspoint.com/plsql/plsql_arrays.htm | Yes | [6 empty] | Yes | No | New Record
22 | MS Project 2013: How to Schedule Your Project Using Calendars | Scheduling is an important element in effectively carrying out and eventually accomplishing a project. In this section, Toby teaches the basic methods of scheduling parameters related to calendars within Project 2013. Every project needs a project calendar, which is the basic time that work is done or is possible to be done on a particular project. In the Change Working Time dialog, it gives a view of the current standard project calendar, which is the default that comes with Project 2013. This, of course, can be changed or modified to suit a specific project that needs a different kind of calendar. Or you can create a new calendar altogether. The calendars in Project 2013 let you define your standard working week, set up your working hours, and plot the public holidays in place as far in advance as you can. | https://www.youtube.com/embed/jVi65g8RPIY | Yes | https://www.youtube.com/embed/B1387aQJPz4 | Yes |  |  |  |  | http://www.tutorialspoint.com/plsql/plsql_conditional_control.htm | Yes | [6 empty] | Yes | No | New Record
23 | MS Project 2013: Scheduling Using Standard Calendar, Holiday, and Exceptions | This video explains how to make a standard calendar for a particular project as well as the corresponding consequences of that. It is important that the calendars of the people working on a project are setup correctly. In fact, it is much better to set your calendar correctly before you start scheduling tasks and resources so that everything in the process is aligned. You can also add some exceptions to the calendar. For instance, for a carpenter, an exception to his working time would be vacations or a couple of weeks off. Of course, public holidays like Christmas and Easter should be added as exceptions in the calendar as well. | https://www.youtube.com/embed/KSH9ADLQDdo | Yes | https://www.youtube.com/embed/IeSGhXHNZGE | Yes |  |  |  |  | http://www.tutorialspoint.com/plsql/plsql_loops.htm | Yes | [6 empty] | Yes | No | New Record
24 | Microsoft Project 2013: Using Earn Value Analysis Tools in MS Project | In this video, learn how to use earn value analysis tools to review the progress of your Microsoft Project 2013 project. | https://www.youtube.com/embed/7Y__rcXwNjw | Yes | https://www.youtube.com/embed/9WGp1m98wlU | Yes |  |  |  |  | http://www.tutorialspoint.com/plsql/plsql_arrays.htm | Yes | [6 empty] | Yes | No | New Record
25 | MS Project 2013: Keyboard Shortcuts and Key tips | This video will give you an alternative to operating Microsoft Project 2013 without using a mouse, and that is through the use of keyboard shortcuts. A helpful tool to let you know the keyboard shortcut of a certain command is called the key tip. It's the small bubble that appears when you hover over a command and describes what the command does and what keyboard shortcut can be used to get it to work. | https://www.youtube.com/embed/3rJfRMNZC6U | Yes | [6 empty] | http://www.tutorialspoint.com/plsql/plsql_constants.htm | Yes | [6 empty] | Yes | No | New Record