## Sheet1
Topic ID | Question ID | Question | Answer01 | Answer01Correct[Yes/No] | Answer02 | Answer02Correct[Yes/No] | Answer03 | Answer03Correct[Yes/No] | Answer04 | Answer04Correct[Yes/No] | Answer Time in Sec | Control Type[Option Or Checkbox] | Active | Deleted | ChangeLog
1 | 1 | __________ Version of Microsoft makes general usage of touch screen. | 2013 | Yes | 2010 | No | 2007 | No | All of the above | No | 30 | Option | Yes | No | New Record
1 | 2 | The ________ is in essence thinking carefully about something before you do it. | Planning | Yes | Testing | No | Collection | No | Executing | No | 30 | Option | Yes | No | New Record
1 | 4 | Microsoft 2013 touch features require touch enabled windows such as _________ | Win 7 / Win 8 | Yes | 2003 | No | 2007 | No | All of the above | No | 30 | Option | Yes | No | New Record
1 | 3 | Microsoft Project 2013 is supported to run on Windows Vista, Windows 7 and Windows 8. | False | Yes | True | No |  |  |  |  | 30 | Option | Yes | No | New Record
2 | 1 | ___________ Feature allows communicating with members of team by instant messaging, video chat, email or phone call. | Talk to Team | Yes | Project Templates | No | Task Path | No | Show Off Project Data | No | 20 | Option | Yes | No | New Record
2 | 3 | ____________ Feature of Microsoft Project can be handy for a project manager handling large and complex schedules. It allows the user to see the path for a specific task including Successors, Driven successors, Predecessors and Driving Predecessors. | Task Path | Yes | Show Off Project Data | No | Talk to Team | No | Project Templates | No | 20 | Option | Yes | No | New Record
2 | 2 | Which of the following statements is true about Microsoft Project's standard (out of the box) Gantt Chart: | It does not show critical path tasks in red, but they can be changed to red or any other color you choose | Yes | It shows critical path tasks in red and cannot be changed | No | It shows critical path tasks in red and can be changed to any color you choose | No | It does not show critical path tasks in red, all tasks are in blue and cannot be changed, but they are shown in red on the tracking Gantt | No | 20 | Option | Yes | No | New Record
3 | 1 | Which operator on the home screen denotes help facilities in Microsoft project? | ? | Yes | / | No | 5 | No | * | No | 10 | Option | Yes | No | New Record
4 | 1 | Which options do start screen provides on starting a project in Microsoft project 2013 | All of the above | Yes | Starting a new blank project | No | Starting projects from templates or other file formats | No | Setting options for new projects | No | 20 | Option | Yes | No | New Record
4 | 2 | On which of these pages of the Project Options in Project 2013 would you find the check box to enable or disable the showing of the Start Screen? | General | Yes | Advanced | No | Display | No | Trust Center | No | 20 | Option | Yes | No | New Record
4 | 3 | Window Area consists of: | List of information in the table & Gantt Chart | Yes | List of information in the table | No | Gantt Chart | No | Ribbon | No | 30 | Option | Yes | No | New Record
4 | 4 | Backstage view consists of: | All of the above | Yes | New | No | Open | No | Save / Save As | No | 20 | Option | Yes | No | New Record
4 | 5 | Which of the following is a split view by default in Project 2013? | Task Entry | Yes | Task Usage | No | Resource Usage | No | Tracking Gantt | No | 20 | Option | Yes | No | New Record
5 | 1 | __________ allows screen positions to be selected with the touch of a finger. | Touch panels | Yes | Image scanner | No | Light pen | No | Mouse | No | 15 | Option | Yes | No | New Record
5 | 2 | Saving a project file in Project 2013 with a "Save as type" of Excel Workbook invokes the Export Wizard. | True | Yes | False | No |  |  |  |  | 30 | Option | Yes | No | New Record
6 | 1 | On which of the main Project 2013 ribbon tabs would you find the Switch Windows command? | View | Yes | Project | No | Task | No | Home | No | 10 | Option | Yes | No | New Record
6 | 2 | What is the easiest way to view the legend for the Gantt chart? | Double click an empty area on the Gantt Chart | Yes | Right click the Gantt Chart and click View Legend | No | On the View tab, click the Legend checkbox | No | On the Format tab, click the Legend checkbox | No | 30 | Option | Yes | No | New Record
6 | 3 | Which of these keys would you use to show and hide the ribbon Key Tips in Project 2013? | Alt | Yes | Ctrl | No | Shift | No | Space | No | 20 | Option | Yes | No | New Record
6 | 4 | Which of the following ribbon tabs is NOT one of the main tabs in Project 2013? | Format | Yes | View | No | Resource | No | Report | No | 20 | Option | Yes | No | New Record
7 | 1 | In Project 2013 the Quick Access Toolbar can be positioned above or below the Status Bar. | False | Yes | True | No |  |  |  |  | 15 | Option | Yes | No | New Record
8 | 1 | Mini Toolbar can be used in both the modes mouse mode and touch mode. | True | Yes | False | No |  |  |  |  | 20 | Option | Yes | No | New Record
8 | 2 | ___________ Action is used to display the mini toolbar. | Right-click | Yes | Double-click | No | Scroll | No | Left-click | No | 30 | Option | Yes | No | New Record
8 | 3 | Which commands do Mini toolbar allows | All of the above | Yes | Commands to change the font | No | Commands to do things like Bold, Italic, Underline | No | Drop down which indicates how complete a particular task is. | No | 30 | Option | Yes | No | New Record
9 | 1 | ___________ Action is used to display the context menu. | Right-click | Yes | Double-click | No | Left-click | No | Scroll | No | 30 | Option | Yes | No | New Record
10 | 1 | Which commands does status bar displays? | All of the above | Yes | Cell Mode | No | Filter | No | AutoFilter | No | 20 | Option | Yes | No | New Record
11 | 1 | Which options does screen tip style in general backstage view displays | All of the above | Yes | Show feature description in screen tips | No | Don’t show feature description in screen tips | No | Don’t show screen tips | No | 15 | Option | Yes | No | New Record
11 | 2 | Which command options does backstage view consists | All of the above | Yes | Scheduling | No | Proofing | No | Trust Centre | No | 10 | Option | Yes | No | New Record
11 | 3 | One can schedule newly created tasks | Automatically & Manually | Yes | Automatically | No | Manually | No |  | No | 30 | Option | Yes | No | New Record
12 | 1 | When using the Assign Resources dialog in Project 2013 you can select multiple resources by holding down the Ctrl key as you click to select them. | True | Yes | False | No |  |  |  |  | 30 | Option | Yes | No | New Record
13 | 1 | While setting task which operator indicates estimated duration in the chart. | ? | Yes | * | No | % | No | & | No | 30 | Option | Yes | No | New Record
13 | 2 | In more recent versions of MS Project such as MS Project 2013 the standard project file extension is .mppx. | False | Yes | True | No |  |  |  |  | 30 | Option | Yes | No | New Record
13 | 3 | A task that is 50% complete means: | Half the duration has been used up | Yes | Half the available resources for the task have been used up | No | Half the work has been done | No | Half the cost of the task has been spent | No | 20 | Option | Yes | No | New Record
14 | 1 | With a fixed work task, if you change the work then: | Duration changes | Yes | Units changes | No | The leveling delay increases | No | You cannot change it, the work is fixed | No | 20 | Option | Yes | No | New Record
14 | 3 | When you add a task between two already linked tasks: | The task is automatically linked by default but you can set the "auto link” inserted or moved tasks" option off to not have them linked automatically | Yes | The task is automatically linked to the preceding and following task but you can manually unlink it | No | The task is not automatically linked to the preceding and following tasks, you needed to link it manually | No | The task is not automatically linked by default but you can set the "auto link” inserted or moved tasks" option on to link them automatically | No | 20 | Option | Yes | No | New Record
14 | 2 | When you add another resource to a fixed work task that already has resources assigned to it then which of the following is true: | You cannot switch off the effort driven indicator, on a fixed work task so the work is always shared unless you manually enter it. | Yes | The existing amount of work will always be shared equally between the resources even if you specify the amount of work the resource is to be allocated | No | The new resource will be assigned the same amount of work as the existing resources, so work will increase | No | The work will be shared between the resources, but if you set the effort driven flag off the new resource will be assigned the work you specify | No | 10 | Option | Yes | No | New Record
14 | 4 | You would like to add a row at the top of your project schedule that rolls up or sums all the information below. What is the easiest way to do that? | Enable the Project Summary Task through the Format tab on the Ribbon. | Yes | Insert a Summary Task at the top of your schedule and indent all tasks below it. | No | Insert a task at the top of your schedule and establish the predecessors appropriately. | No | Enable the Project Summary Task through Project tab and Project Information. | No | 20 | Option | Yes | No | New Record
14 | 5 | One way of showing only the critical tasks in a project is to apply the Critical filter from the View tab on the Project 2013 ribbon. | True | Yes | False | No |  |  |  |  | 20 | Option | Yes | No | New Record
14 | 6 | How would you configure Microsoft Project to display the Project Summary for all new projects? | The Show Project Summary Task checkbox via the Advanced Project Options | Yes | The Show Project Summary Task checkbox via the Schedule Project Options | No | Project Summary Task checkbox via the FORMAT tab | No | Project Summary Task checkbox via the VIEW tab | No | 30 | Option | Yes | No | New Record
14 | 7 | Which of the following is NOT a Report category? | Schedule | Yes | Dashboards | No | Resources | No | In Progress | No | 20 | Option | Yes | No | New Record
14 | 8 | Which of the following is NOT one of the standard options in the Project 2013 Zoom dialog? | 1 year | Yes | 1 week | No | 1 month | No | Entire project | No | 20 | Option | Yes | No | New Record
15 | 1 | Project options are displayed in _____________ view. | Backstage | Yes | Workspace | No | Start Screen | No | None of the above | No | 15 | Option | Yes | No | New Record
15 | 2 | In Project 2013 where would you find the Update Project command button? | On the Project tab in the Status group. | Yes | On the Project tab in the Tracking group. | No | On the Task tab in the Schedule group. | No | On the View tab in the Data group. | No | 30 | Option | Yes | No | New Record
15 | 3 | In project options, Work is entered in ___________. | All of the above | Yes | Hours | No | Days | No | Minutes | No | 10 | Option | Yes | No | New Record
15 | 4 | In Project 2013 the duration of a summary task is the duration from the earliest start date of any of its subtasks to the latest finish date of any of its subtasks. | True | Yes | False | No |  |  |  |  | 30 | Option | Yes | No | New Record
15 | 5 | In Project 2013 the timescale can be shown with up to 3 tiers. | True | Yes | False | No |  |  |  |  | 20 | Option | Yes | No | New Record
15 | 6 | Which of these built-in tables in Project 2013 includes the Actual Start Date and Actual Finish Date by default? | Tracking | Yes | Entry | No | Cost | No | Work | No | 20 | Option | Yes | No | New Record
15 | 7 | Which are the advanced properties in project? | Summary | Yes | Statistics | No | Contents of project | No | None of the above | No | 15 | Option | Yes | No | New Record
16 | 1 | Which of the following is default dependency type when you link tasks: | finish to start | Yes | start to finish | No | start to start | No | finish to finish | No | 20 | Option | Yes | No | New Record
16 | 2 | Which key is used to link two tasks in project | ctrl + z | Yes | shift+ z | No | ctrl + T | No | ctrl + L | No | 30 | Option | Yes | No | New Record
17 | 1 | Which view allows you to see all tasks assigned to a single Resource? | The Resource Form | Yes | The Task Form | No | The Task Sheet | No | The Resource Sheet | No | 30 | Option | Yes | No | New Record
17 | 2 | Which of the following is NOT one of the tabs in the Project 2013 Organizer? | Resources | Yes | Reports | No | Maps | No | Filters | No | 30 | Option | Yes | No | New Record
17 | 3 | Which of the following is NOT a Resource Type in Microsoft Project 2013? | Labor | Yes | Material | No | Cost | No | Work | No | 20 | Option | Yes | No | New Record
17 | 4 | Which view helps visually display resources that are over allocated via vertical bar graph? | The Resource Graph | Yes | The Resource Sheet | No | The Team Planner | No | The Resource Usage | No | 15 | Option | Yes | No | New Record
17 | 5 | I am adding a new resource to a project in Project 2013. The resource is fuel for a motor. In which column on the Resource Sheet would I specify that the units for this resource are gallons? | Material Label | Yes | Std. Rate | No | Accrue at | No | Initials | No | 10 | Option | Yes | No | New Record
17 | 6 | Which of the following is NOT one of the standards Accrual At options in Project 2013? | Level | Yes | Prorated | No | Start | No | End | No | 30 | Option | Yes | No | New Record
18 | 1 | ___________ Action is used to assign resources to the task. | Right-click & Click Assign Resources | Yes | Double-click & Click Assign Resources | No | Scroll & Click Assign Resources | No | Left-click & Click Assign Resources | No | 30 | Option | Yes | No | New Record
18 | 2 | All of the following are false except: | You cannot assign the same resource more than once to a task unless you use resource contouring | Yes | Max units limits the number of resources you can assign to a task | No | Resources must be added to the resource sheet before they are assigned to a task | No | Resources on the critical path are shown in red | No | 30 | Option | Yes | No | New Record
18 | 2 | You click on the Resource Sheet view and notice that one of the resource names appears in Red. What does this mean? | The resource is over-allocated | Yes | The name is misspelled | No | The resource is not assigned to any tasks | No | The resource has not been properly added to the Resource Sheet | No | 30 | Option | Yes | No | New Record
18 | 3 | When using the Project 2013 Gantt Chart Wizard which of these is NOT one of the options for the task information to display with the Gantt bars? | Work | Yes | Dates | No | Resources | No | None of the above | No | 20 | Option | Yes | No | New Record
18 | 4 | When using the Assign Resources dialog in Project 2013 you can select multiple resources by holding down the Ctrl key as you click to select them. | True | Yes | False | No |  |  |  |  | 20 | Option | Yes | No | New Record
19 | 1 | When using Project 2013 you can only have one project file open at a time. | False | Yes | True | No |  |  |  |  | 20 | Option | Yes | No | New Record
19 | 2 | Open new project tab is displayed in _____________ view. | Backstage | Yes | Workspace | No | Start Screen | No | None of the above | No | 10 | Option | Yes | No | New Record
19 | 3 | On which of the main Project 2013 ribbon tabs would you find the Switch Windows command? | View | Yes | Project | No | Task | No | Home | No | 20 | Option | Yes | No | New Record
19 | 4 | In how many ways we can close individual project windows | 2 | Yes | 1 | No | 3 | No | None of the above | No | 20 | Option | Yes | No | New Record
20 | 1 | Tasks on a project's critical path have negative slack. | False | Yes | True | No |  |  |  |  | 30 | Option | Yes | No | New Record
21 | 1 | You are in the process of creating a new schedule in Microsoft Project. You want to ensure that all tasks added to the schedule will be “Auto Scheduled”. What should you do? | Under Schedule Options, set New tasks created to “Auto Scheduled” | Yes | Under Advanced Options, set New tasks created to “Auto Scheduled” | No | Use the Task Mode field within the Gantt Chart view to change the value to “Auto Scheduled” | No | Highlight all tasks and use the “Auto Schedule” button | No | 20 | Option | Yes | No | New Record
22 | 1 | In Microsoft Project which of the following describes the capability of calendars? | You can assign different project calendars to different resources, and you can assign calendars to tasks | Yes | There is only one project calendar and all resource calendars are derived from this | No | You can have multiple project calendars, the base calendar is assigned to resources, but you can assign a different calendar to a resource, you cannot assign a calendar to a task | No | You can assign calendars to tasks, resources and allocations | No | 20 | Option | Yes | No | New Record
22 | 2 | Which view would you use for comparing your project schedule to the baseline? | Tracking Gantt | Yes | Gantt Chart | No | Leveling Gantt | No | Network Diagram | No | 15 | Option | Yes | No | New Record
22 | 3 | ___________ Times are assigned to tasks when you enter a start or finish date without specifying a time. | Default Start & End Time | Yes | Start Time | No | End Time | No | None of the above | No | 30 | Option | Yes | No | New Record
22 | 4 | Which numbers in calendar are used for cost scheduling and financing. | I. Hours per day II. Hours per week III. Days per month | Yes | I. Hours per week II. Hours per month III. Hours per year | No | I. Hours per day II. Hours per week III. Hours per month | No | I. Hours per day II. Days per week III. Days per month | No | 10 | Option | Yes | No | New Record
22 | 5 | In which tab change working time dialog appears | Project | Yes | Resource | No | Report | No | View | No | 30 | Option | Yes | No | New Record
23 | 1 | Which of the following is the default calendar in Project 2013? | Standard | Yes | Day Shift | No | Night Shift | No | 24 Hours | No | 20 | Option | Yes | No | New Record
23 | 2 | When setting up a Calendar exception in Project 2013, which of the following is NOT one of the time periods that a recurrence pattern can be based on? | Quarterly | Yes | Yearly | No | Monthly | No | Weekly | No | 20 | Option | Yes | No | New Record
23 | 3 | Which of the following is NOT one of the standard calendars in Project 2013? | Day Shift | Yes | Standard | No | Night Shift | No | 24 Hours | No | 15 | Option | Yes | No | New Record
23 | 4 | We can define exceptions for individual resources. | True | Yes | False | No |  |  |  |  | 20 | Option | Yes | No | New Record
23 | 5 | Holiday in calendar is repeated probably on _________ basis. | Annual | Yes | Daily | No | Weekly | No | Monthly | No | 30 | Option | Yes | No | New Record
23 | 6 | Which of these is also known as BCWS (Budgeted Cost of Work Scheduled)? | PV (Planned Value) | Yes | EV (Earned Value) | No | SV (Schedule Variance) | No | AC (Actual Cost) | No | 30 | Option | Yes | No | New Record
24 | 1 | In Project 2013 what is the normal purpose of the F1 keyboard function key? | Invoke help | Yes | Create a new project | No | Save the current project | No | Identify the critical path in the current project | No | 30 | Option | Yes | No | New Record
25 | 1 | Which key is used to assign resources to tasks | Alt + F10 | Yes | Alt + F9 | No | Alt + F8 | No | Alt + F7 | No | 20 | Option | Yes | No | New Record
25 | 2 | _________ Key is used to open a second window for your document to work in different places at same time. | Alt + Shift + F1 | Yes | Alt + Shift + F2 | No | Alt + Shift + F3 | No | Alt + Shift + F4 | No | 15 | Option | Yes | No | New Record
25 | 3 | _______ Key is used to open calculate project dialog. | Alt + J | Yes | Alt + A | No | Alt + H | No | Alt + M | No | 10 | Option | Yes | No | New Record